# Milestone 1 — Delivery Plan & Status

Milestone 1 ("the reliability spine") is split into three sub-milestones. The day ranges map to the build guide's 2-week sequence.

| Sub-milestone | Days | Scope |
| --- | --- | --- |
| M1.1 — Foundation & Data Layer | 1–3 | Schema + Prisma migrations, availability templates, materialized slots, state machine, DB-level constraints |
| M1.2 — Booking Core & Concurrency | 4–7 | Row-level locking (SELECT … FOR UPDATE), reservation expiry worker + sweep, core booking flow end-to-end, admin CRUD |
| M1.3 — Payments, Verification & Delivery | 8–14 | Pix + card integration, signature-verified idempotent webhooks, expiry/payment race handling, concurrency + webhook test suites, deployment (Railway/Render), docs + Postman collection, final hardening |

The four client acceptance criteria (no double booking, reliable expiry release, end-to-end Pix + card in sandbox, reproducible setup) are proven in M1.3 but enabled by the constraints and state machine laid down in M1.1.

## Environment note (verification on this machine)

This dev machine has no Node/Docker preinstalled and its D: drive blocks native-binary writes (Defender). Verification therefore runs from a C: mirror with a portable Node 22 and a portable PostgreSQL 16 (no admin). One hard limit: Prisma's Rust query engine crashes on this CPU (0xC000001D illegal instruction / 0xC0000409 stack overrun, on both library and binary engines). That means the Prisma-based server and the Prisma integration tests (test:integration) cannot run here — they run in CI / on Railway/Render, where the Linux engine is fine.

To prove the runtime guarantees on this box regardless, the two critical behaviours are demonstrated with the pure-JS pg driver running the identical SQL the app uses:

| Proof | Command | Result |
| --- | --- | --- |
| Concurrency (criterion #1) | npm run verify:locking | ✅ 50 contenders × 20 rounds — every round exactly 1 success, 49 clean losses, 0 errors |
| Expiry release (criterion #3) | npm run verify:expiry | ✅ expired→freed, not-due→untouched, paid→never released |

## M1.1 — Foundation & Data Layer — status: ✅ VERIFIED

Delivered in this sub-milestone:

- Project scaffold (TypeScript, ESM, npm scripts, Docker Postgres, env template).

- Prisma schema: Doctor, AvailabilityTemplate, AppointmentSlot, Reservation, Payment, WebhookEvent, EventLog, plus the three status enums.

- init migration (all tables, indexes, FKs) authored to match the schema.

- hard_constraints migration — the guarantees Prisma can't express:

  - one_live_slot_hold partial unique index (a slot holds ≤ 1 live claim).

  - no_overlap_per_doctor GiST exclusion constraint (needs btree_gist) — a doctor can never have two overlapping slots.

- Config plumbing: zod-validated env loader, pino logger (with secret redaction), Prisma client singleton, transactional logEvent helper.

- Reservation/slot state machine encoded as data (canTransition / assertTransition) + full unit-test coverage of legal & illegal moves.

- Availability templates → slot materialization: pure slot math (iterateSlots) + idempotent DB upsert (materializeSlots) over a rolling SLOT_MATERIALIZATION_WEEKS window, with limited-Sunday-hours handling.

- Unit tests for slot math (spacing, custom slot length, trailing-partial drop, narrow Sunday window, empty/inverted windows).

- Idempotent seed (demo doctor + weekday/Saturday/Sunday templates + materialized slots).

Verified: unit tests (12/12), full tsc --noEmit, migrations applied to a real Postgres, and the two hard constraints observed rejecting bad data (overlapping slot → rejected by no_overlap_per_doctor; duplicate (doctorId, startsAt) → rejected by the unique index; non-overlapping → accepted).

## M1.2 — Booking Core & Concurrency — status: ✅ code complete, core guarantees proven

Delivered:

- reserveSlot — raw SELECT … FOR UPDATE inside a Prisma interactive transaction, with lock-wait tx options tuned for concurrent bursts.

- Concurrency proven: 50 × 20 rounds, exactly one winner every round (npm run verify:locking).

- Expiry: releaseReservation (locked re-check), periodic sweep, precise pg-boss scheduleExpiry, and the worker.ts entrypoint wiring all three plus nightly materialization. Release logic proven across all three cases (npm run verify:expiry).

- Reservation service (reserve + best-effort schedule; sweep is backstop).

- Patient booking API — GET /api/doctors, GET /api/slots, POST /api/reservations, GET /api/reservations/:id, payment-start stub (501 until M1.3), plus /healthz + /readyz.

- Admin CRUD behind an API-key guard — doctors, availability templates, on-demand materialize.

- Central error handling (409 for lost races, 400 for bad input, never 500), zod validation, async handler wrapper.

- Prisma integration tests authored (tests/integration/reserve-race, tests/integration/expiry) for CI/deploy where the Prisma engine runs.

- Whole M1.2 tree typechecks clean (tsc --noEmit exit 0).

Not runnable on this machine: the Express server and test:integration (both need the Prisma runtime — see the environment note above). They are typechecked here and run in CI / deployment.

## M1.3 — Payments, Verification & Delivery — status: 🟡 payment layer complete + proven; finalization pending

Provider chosen: AbacatePay (Pix-first). Built provider-agnostic so only the concrete adapter changes when sandbox keys arrive.

Delivered + proven:

- Swappable PaymentProvider interface + AbacatePay adapter skeleton (endpoints/fields/signature scheme marked TODO(sandbox)) + in-memory MockProvider + provider registry.

- HMAC-SHA256 raw-body signature verification (constant-time compare).

- startPayment — stable idempotency key per (reservation, method); one Payment row; provider-idempotent charge.

- Signature-verified, idempotent webhook handler with the full exception matrix, all under the same row lock the expiry job uses.

- Raw-body webhook route mounted before express.json(); real payment-start route; 401 on tampered signatures; 409 on unpayable reservations.

- Proven on this box (npm run verify:webhook): idempotency (5× sequential + 5× concurrent → confirm once, charge once), out-of-order convergence, tampered-signature rejection, and the payment-at-expiry race consistent across 50 rounds (always Paid+Approved OR freed+Refunded — never paid-but-unbooked).

- Prisma integration tests authored (tests/integration/webhook) for CI.

- Whole tree + tests typecheck clean (tsc --noEmit, tsc -p tsconfig.test.json).

Finalization still to do (the PDF's close-out phase):

- Wire the AbacatePay adapter against the real sandbox (needs API keys) and run one live Pix + one live card end-to-end with captured evidence.

- Security hardening: helmet, express-rate-limit on reserve/payment, HTTPS-only in prod, DB least-privilege role.

- k6 load suite in CI + docs package (SCHEMA.md, API.md, WEBHOOKS.md, DEPLOYMENT.md) + Postman collection.

- Deploy web + worker to Railway/Render; reproducibility check on a clean machine; client acceptance walkthrough + written sign-off.